Mental Health Charter for Sport and Recreation

The next steps…

Action plan template for community & grassroots clubs & groups

As a signatory of the Mental Health Charter for Sport and Recreation we are committed to taking action across the following six areas:

- Use our sport to promote good mental health and wellbeing

- Adopt good mental health policies and best practices

- Appoint ambassadors and role models

- Tackle discrimination on the grounds of mental health

- Support a pan-sport platform to develop and share resources and best practice

- Throughout all of this we should regularly monitor our performance

To help facilitate a joined-approach we have appointed a lead staff member:

Name:

Position:

Tel:

Email:

Organisation website:

Our action plan is set out below.

[Add date and version number]

| Audience | Activity description (the numbers next to the activity description heading correspond with the Charter’s areas of activities listed above) | Support required | Internal lead (include contact details) | Timescale | How will we measure success? | Progress update (leave blank for now, we recommend you update this at 6 and 12 months) |
| --- | --- | --- | --- | --- | --- | --- |
| All | Raising awareness: Create introductory website and intranet pages (1&2) - What is the Charter and why we have signed it? - What we have done so far as a club. Links to case-studies and tips sheet - Information and links about mental health – e.g. links to local mental health services - Useful contacts including employee assistance programme and relevant policies (Intranet only) | - Key messages about the Charter - Links to Mental Health awareness | Communications officer commsofficer@club.com | Content created – June. Published – July To be updated at key milestones | Pages live. Number of downloads. |  |
| All | Charter action plan working group Establish an action plan working group including: Director / trustees /governance/chairperson/committee member HR / volunteer coordinator Person responsible for marketing and communications Club representatives e.g. coaches, personal trainers, leaders Local partners if appropriate The working group will: Review action plan and map out what exists already, identify synergies and gaps for new activities Assign lead members Review progress against action plan and agree evaluation activities | N/A | Project manager clive@club.com | First meeting booked for the 15 June 2015. Subsequent meetings scheduled monthly. | Outputs against agreed actions at the meeting. Success of activities. Other measures through annual staff survey. |  |
| All | Raising awareness – keeping the wider community up-to-date (1,2&5) Secure regular slots in the following: Membership newsletter (volunteer / athletes) Workforce e-newsletters (volunteers / coaches and officials) Information on noticeboards Articles in local papers about project successes | Updates on new resources and activities | Communications officer commsofficer@club.com | Request to editors – June Schedule copy reminders. Monthly / quarterly as appropriate | Web analytics following publication. |  |
| Other clubs and wider sector | Share good practice (5) Contact other local clubs to share good practice and see if any potential joined-up working. Tell your local council / Health and Wellbeing Board what you’re doing. Contact the governing body to ask them to promote the project. Share good practice with Mind so that it can be considered as a resource on the Mental Health Charter for Sport and Recreation’s website. | N/A | Project manager clive@club.com | Equality leads meeting scheduled 15 June 2015. | Number of things done differently as a result. Impact of changes. Opportunities for joined up working. |  |
| All | Ambassadors and role models (3) Recruit a range of ambassadors and role models who are willing to support the Charter including those who have personal experience /close experience and those who can champion the programme to include: Director / Trustee Coaches / volunteers (work with workforce development) Participants Ambassadors and champions to support with: Mental health selfies Speaking to stakeholders Case studies Local media Attendance at events | Ambassador guidance | Communications officer commsofficer@club.com | i) Create a brief for ambassadors / role models - June ii) Recruitment and briefings – early July iii) Engagement of ambassadors and role models in internal / external comms – mid July onwards | Reach of coverage. Feedback from stakeholders. |  |
| Employees | Raising awareness: Internal awareness raising campaign (1,2&4) Work with colleagues to raise awareness of the Charter and how to promote positive mental well-being and reduce discrimination through: forums – Charter and well-being to be a regular agenda item at meetings Create a presentation accessing existing resources including Time to Talk videos for team managers/coaches/leaders to use Include regular information in e-newsletter Posters and literature to be available in shared areas: kitchens, meeting rooms, changing rooms, bar etc | Any supporting materials | Communications officer commsofficer@club.com Head of HR – hr@club.com | June – Charter why we have signed / case studies what we have available already (employee assistance / flexible working policy etc.) July - It’s good to talk. Let’s end discrimination August – How to promote positive mental well-being September – October – World Mental Health Day | Improvements recorded through staff survey. |  |
| Wider community | World Mental Health Day Awareness (weekend) event Deliver activity to promote World Mental Health Day: Produce press release about what’s going on Sharing of videos and mental health selfies / video case studies at appropriate times e.g. half time, in the club house etc. Invite local Mental Health services to get involved and build relationships Utilise ambassadors and champions |  | Communications officer commsofficer@club.com | October 9 – 11th | Reach of coverage during the event |  |

If you are communicating externally, it’s important that you have a look at our guidance on the most appropriate language and photo images to use. We have provided information and key messages on the Sport and Recreation Alliance’s website.

You can see details of other organisations who have signed up here.

We hope you will be proud of your action plan and tell your staff and networks about it!

Checklist:

( You have completed the action plan and shared it across your club or group

( Written a website summary of your activity

( Set regular dates to review the action plan

# Text boxes

Add your logo here

Add in here a short statement on what inspired you to sign the Charter and why mental health is important to your organisation e.g. We’re already piloting a mental health programme and are committed to supporting our sport to tackle stigma around mental health.